To: Prof. Isaac Chuang
From: Nancy Ouyang, Cappie Pomeroy (MIT MechE 2013)
Date: 9 September 2013

6.01x Robot Kit Proposal

We propose designing a robot that will:
- Cost $150 in quantity one
- Accept motor voltage levels (be able to drive straight) and output 2 to 3 distance readings at 12 times per second
- Communicate wirelessly with SOAR
- Be wirelessly programmable with up to 40 robots in a single room
- Have a light tracking head that interfaces with existing 6.01 programs to create a light-tracking robot
- Full documentation and release of source files as open source hardware by Dec. 20th

[REDACTED]

Detailed Schedule
12 Weeks
[REDACTED]

1st month deliverable: robot interfacing with SOAR
1. Order parts
2. Parts arrive. 1st iteration robot driving straight (possibly with odometry)
  1. Evaluate and compare CPUs: Beaglebone, Arduino, ARM
  2. Evaluate and compare drive systems: continuous rotation servos, gearmotors
  3. Evaluate and compare odometry systems: rotary encoders, shaft encoders, ir break beam
3. 1st iteration robot outputting accurate distance readings
  1. Evaluate and compare sonar, IR, photoresistor for distance readings
4. 2nd robot iteration for desired features such as ease of assembly
2nd Month deliverable: Light following robot, documentation
1. Light tracking head first iteration
2. Light tracking head communicating with SOAR to create "pet robot" that follows light
3. 2nd iteration of light tracking head for desired features
4. Document robot+light tracking head system
3rd Month deliverable: Wireless robot (two complete systems), documentation
1. Evaluate and compare wireless systems (nRF, xbee, bluetooth) for classroom environment
2. Wirelessly transmit and receive motor voltage levels and distance readings (interface with SOAR)
3. Wireless interface for light tracking head-and-robot system
4. Assemble two complete systems and document system. Release source files under the TAPR open hardware license (http://www.tapr.org/OHL) to github or other suitable repository.

Quote
[REDACTED]

Additional Details
[REDACTED]

We will license all our hardware work under the TAPR open hardware license (http://www.tapr.org/OHL) to github or other suitable repository, and any software work under GPL.

[REDACTED]

Materials Budget
$1500
Roughly broken down into: $200 express shipping, $600 prototyping one robot and a few partial ones, $400 building two robots, $300 equipment and consumables (wire etc.).

Detailed Prototyping Budget
Sensors			Quantity 1
IR sensor	Sharp GP2Y0A02YK0F	https://www.sparkfun.com/products/8958	14.95
Short Range IR	Pololu 38kHz range finder	http://www.pololu.com/catalog/product/2460	5.95
Sonar Sensor	Maxbotix LVEZ1	https://www.adafruit.com/products/172#Description	24.95
Odometry	EVE-GA1F1724B	http://www.digikey.com/product-detail/en/EVE-GA1F1724B/P10859-ND/286883	0.64

Wireless
nRF uC	nRF24L01+ breakout	https://www.sparkfun.com/products/691	19.96
nRF USB	nRF24LU1+ breakout	http://www.seeedstudio.com/depot/crazyradio-24ghz-nrf24lu1-usb-radio-dongle-with-antenna-bccr01a-p-1525.html	33
Xbee uC	XB24-Z7WIT-004	http://www.digikey.com/product-detail/en/XB24-Z7WIT-004/602-1098-ND/1942304	17
Xbee USB	XBee Explorer USB + XBee	https://www.sparkfun.com/products/8687	41.95
Bluetooth uC	BlueSMiRF Silver	https://www.sparkfun.com/products/10269	39.95
Bluetooth USB	Bluetooth USB 2.0 Micro Adapter Dongle	http://www.amazon.com/Bluetooth-USB-Micro-Adapter-Dongle/dp/B001EBE1LI/ref=pd_sxp_f_pt	1.55

uC
Arduino	Arduino Leonardo	https://www.adafruit.com/products/849	24.95
Beaglebone	BeagleBone Black	https://www.adafruit.com/products/1278	45
ARM	Stellaris LM4F120 LaunchPad	http://www.mouser.com/ProductDetail/Texas-Instruments/EK-LM4F120XL/?qs=sGAEpiMZZMsf26MmFqIJrHG9DD2FkafK0BkW7bdObZ0=	10.99

Chassis
Sain Smart	4WD Aluminum mobile robot platform	http://www.sainsmart.com/sainsmart-4wd-drive-aluminum-mobile-robot-platform-for-robot-arduino-raspberry-pi-gold.html	45.99
Robot Mesh	2WD miniQ	http://www.robotmesh.com/2wd-miniq-robot-chassis?gclid=COX8jLOIv7kCFYqZ4Aodcz8AxQ	34.3
DFrobot	Turtle-2WD mobile platform	http://www.dfrobot.com/index.php?route=product/product&product_id=65	41

Motor Controllers
TI	SN754410NE	http://www.mouser.com/ProductDetail/Texas-Instruments/SN754410NE/?qs=sGAEpiMZZMvbYnN5EaJWBDjbQCgliZjvodpiuLF/Ays=	2.34
ST	L298N	http://www.digikey.com/product-detail/en/L298N/497-1395-5-ND/585918	4.67

		Total	409.14